## Product Backlog
ID | Product Backlog Item Description | Priority | Initial Estimation | Adjustment Factor | Adjusted Estimate | Done
1 | Ability to log in | 2 | M |  |  | ✔
2 | Ability to log in as admin | 3 | S |  |  | ✔
3 | Main page GUI | 1 | L |  |  | ✔
4 | User configuration | 4 | L |  |  | ✔
5 | View passengers by flight | 2 | S |  |  | ✔
6 | View all flights | 1 | S |  |  | ✔
7 | View passenger details | 1 | S |  |  | ✔
8 | Set up database | 1 | L |  |  | ✔
9 | View passenger overall risk | 2 | S |  |  | ✔
10 | View flights by risk | 2 | S |  |  | ✔
11 | Detailed searches (more constraints) | 4 | L |  |  | ✔
12 | View passenger risk analysis (Risk scorecard) | 2 | S |  |  | ✔
13 | Create new rules and risk profiles | 3 | M |  |  | ✔
14 | create and save user specific queries | 3 | M |  |  | ✔
15 | create and populate shared folders | 4 | L |  |  | ✔
16 | admin can restrict certain information | 3 | S |  |  | ✔

## Sprint 1
Sprint 1 |  | Team member | Not Started | In progress |  |  | Done
|  |  |  | Design | Development | Testing
1 | Main page GUI - Front end | Dan |  |  |  |  | ✔
1.1 | Flights page | [5 empty] | ✔
1.2 | Passengers page | [5 empty] | ✔
1.3 | Home | [5 empty] | ✔
2 | View all flights - back end | Kris |  |  |  |  | ✔
2.1 | add flights | [5 empty] | ✔
2.2 | Query flights | [5 empty] | ✔
2.3 | Display results | [5 empty] | ✔
3 | View passenger details - Back end | Greg |  |  |  |  | ✔
3.1 | Add Passengers | [5 empty] | ✔
3.2 | Query passengers - Back end | [5 empty] | ✔
3.3 | Display results | [5 empty] | ✔
4 | Set up database | Rhys |  |  |  |  | ✔
4.1 | Flights table - Back end | [5 empty] | ✔
4.2 | Passenger table | [5 empty] | ✔
4.3 | Risks table | [5 empty] | ✔
4.4 | Plane type | [5 empty] | ✔
5 | View passengers by flight | Josh
Release 1

## Sprint 2
Sprint 1 |  | Team member | Not Started | In progress |  |  | Done
|  |  |  | Design | Development | Testing
1 | Risk GUI | Dan |  |  |  |  | ✔
1.1 | View flights by risk | [5 empty] | ✔
1.2 | View passenger overall risk | [5 empty] | ✔
1.3 | View passenger details | [5 empty] | ✔
1.4 | Integration of back end code | [5 empty] | ✔
2 | Risk Queries | Kris |  |  |  |  | ✔
2.1 | Query flights by risk | [5 empty] | ✔
2.2 | User configuration | [5 empty] | ✔
2.3 | Query Passenger's overall risk | [5 empty] | ✔
3 | Back end query and code | Greg |  |  |  |  | ✔
3.1 | Query passenger details | [5 empty] | ✔
3.2 | Code to login User | [5 empty] | ✔
3.3 | Code to login authenticated Admin | [5 empty] | ✔
3.4 | Detailed searches (more constraints) | [5 empty] | ✔
4 | Back end query and code | Rhys |  |  |  |  | ✔
4.1 | Create new rules and risk profiles | [5 empty] | ✔
4.3 | admin can restrict certain information | [5 empty] | ✔
4.4 | create and save user specific queries(different stuff authenticated users can do) | [5 empty] | ✔
5 | Create and populate shared folders | Josh | ✔
5.2 | Shared folders | Josh | ✔
Release 1